## Plan
Story | What | Points | Wave | Verdict
STRY0067504 | Adaptive: Outbound REST Message | 4 | 1 - Test now | Ready after small edits
STRY0067506 | Adaptive: Data Sources + staging tables | 8 | 1 - Test now | Rework: cut to Project/Task/Demand first
STRY0066697 | Adaptive: Project transform map | 7 | 1 - Test now | Ready after small edits
STRY0066699 | Adaptive: Project Task transform map | 7 | 1 - Test now | Ready after small edits
STRY0066695 | Adaptive: Demand transform map | 7 | 1 - Test now (once Demand rule is known) | Fix financial fields
STRY0065263 | Asana: Project transform map | 7 | 1 - Test now | Rework: conflicts with new HR form
STRY0065275 | Asana: Project Task transform map | 7 | 1 - Test now | Blocked: no Task IDs in export
NEW-1 | Mock Load 1 in Dev + count check | 3 | 1 - Test now | Add
STRY0066718 | Adaptive: Risks | 4 | 2 | Small edits
STRY0066715 | Adaptive: Issues | 4 | 2 | Small edits
STRY0067099 | Adaptive: Lessons Learned | 5 | 2 | Confirm target fields
STRY0066701 | Adaptive: Status reports | 5 | 2 | Add to Data Source story
NEW-2 | Adaptive: Task dependencies | 3 | 2 | Add (if dependencies are in scope)
STRY0066721 | Adaptive: Budgets -> cost plans | 6 | 3 | Confirm scope + fields
STRY0066702 | Adaptive: Rates, resources, time cards | 15 | 3 | Split into 3; confirm scope
STRY0066723 | Attachments (manual) |  | 3 / cutover | Point it; confirm volume

## Findings
Severity | Story | Finding | Fix
Blocker | All Adaptive | Several stories say an 'upstream pipeline' converts values before they reach ServiceNow (66695, 66697, 66715, 66721, 66702). With the REST pull there is no upstream pipeline: the Data Source loads raw Adaptive values. | Decide one place for conversions. Recommended: the Data Source script only flattens JSON; every value conversion (state, phase, priority, RAG, Capex/Opex) lives in the transform map (field map script or onBefore). Remove 'upstream pipeline' wording from the stories.
Blocker | All Adaptive | The correlation_id format differs between stories: 'Adaptive ID column' (66697), full id string '/C_PMOLessonsLearned/123' (67099), and the agreed standard 'ADAPTIVE:' + SYSID. API reference fields (Parent.id, C_RelatedWorkItem.id) return the internal id path, not the SYSID. | One rule, written once in 67506 and referenced everywhere: correlation_id = 'ADAPTIVE:' + API id (e.g. ADAPTIVE:/Project/abc123). Parent and related-item columns use the same rule, so child lookups match without a second query.
Blocker | 67506, 66695 | The Demand vs Project rule is still undefined, so the Demand and Project CZQL queries cannot be written. | Get the rule. Until then, test with Projects only.
Blocker | 67506 | No in-flight filter is stated. Without a WHERE clause the pull returns every project ever created in Adaptive. | State the Adaptive State values in scope (e.g. Active, On Hold, Draft?) in the story.
High | All | Several stories point to guides that are not attached here (Adaptive_to_ServiceNow_Mapping_Guide, RIDAC and Resource mapping guides), so the field lists could not be checked. | Attach them to the stories; send them over if you want them reviewed.
Medium | STRY0067504 | Endpoint hard-codes api2.clarizen.com. Adaptive tenants sit on different data centers. | Use the URL returned by authentication/getServerDefinition. Add a second method, metadata/describeEntities, so the dev can read real field names.
Medium | STRY0067504 | The service account key is not issued yet; this blocks the 200 OK check. | Build and test in Dev with the current key only if the client allows it; then swap the credential record. Nothing else changes.
High | STRY0067506 | Covers Projects, Demands, Tasks, Lessons, Risks, Issues, but not Milestones, status reports, budgets, rates/resources/time or dependencies. Stories 66699 (milestones), 66701, 66721, 66702 have nothing to load. | Wave 1: Project, Task, Milestone (and Demand once the rule exists). Add the rest in a follow-up story with the wave 2/3 maps.
High | STRY0067506 | Paging is not mentioned. /data/query returns pages; without paging only the first page loads. | AC: script loops while paging.hasMore is true; staging row count equals the Adaptive count.
Medium | STRY0067506 | People fields: the transform maps resolve users by email, but the API returns user ids. | AC: CZQL selects the dot-walked email (e.g. ProjectManager.Email, C_BusinessOwner.Email) into a flat column.
Medium | STRY0067506 | 8 points for 6 entities plus parsing. | Fine once cut to the wave 1 entities.
Medium | STRY0066697 | Custom field list omits u_executive_sponsor, which the Demand map includes. The story says the two maps must match. | Add u_executive_sponsor, or remove the 'identical' wording.
Medium | STRY0066697 | u_sites needs a script (names -> sys_ids) and the target table for Sites is not stated. | Ask the implementation team which table u_sites references; put it in both 66695 and 66697.
Low | STRY0066697 | State values are not listed. | Add the Adaptive -> ServiceNow state table to the story.
Medium | STRY0066699 | Milestones are a separate Adaptive entity (Milestone), not a flag on Task. | Query Milestone in 67506 and load it through the same map with milestone = true.
Medium | STRY0066699 | Parent lookup fails if a child loads before its parent. | AC: rows load parent-first (sort by WBS level), or run the load twice.
Low | STRY0066699 | State mapping not listed. | Add the Adaptive task state table to the story.
High | STRY0066695 | Total Budget is mapped to financial_return. That field holds the expected return, not a budget. | Confirm the demand budget fields in the dictionary and correct the target.
Medium | STRY0066695 / 66721 | If cost plans are also loaded on the demand, ServiceNow rolls them up and overwrites the directly mapped Capex/Opex totals. | Pick one: map totals on the demand, or load cost plans. Not both.
Blocker | STRY0065263 / 65275 | The Asana CSVs have no Task ID, so correlation_id (the coalesce field) has no source. Parent task and Blocked By hold task names, which are not unique. | Ask the Asana owner for a re-export with Task ID (standard in Asana CSV exports) before building these maps.
High | STRY0065263 | Parent task -> parent project. In the HR portfolio file, rows with a Parent task are the 17 workstreams; they are project tasks, not projects. | Load top-level rows only as projects; send child rows to the task map.
High | STRY0065263 | Section/Column -> primary_portfolio. The new HR form has Functional Area (u_functional_area), whose choices match 11 of the 18 sections. | Decide: Section -> u_functional_area (Q1/Q2 in the mapping workbook).
High | STRY0065263 | Entity/Organization -> u_business_category. The new HR form has no u_business_category; values (BSMH, RSFH, GBS) look like Sites. | Decide per Q4 in the mapping workbook.
High | STRY0065263 | Strategy Timeline -> primary_goal and Strategy Focus -> primary_goal.strategy. Values like 'Long-Term' are not goals, and a transform map cannot set a dot-walked field. | Decide per Q9; likely description or not migrated.
High | STRY0065263 | HR Cross-Impacts -> impacted_business_units. Values (AVP, Skills, Labor...) are not Business Units; the map would reject or blank them. | Decide per Q10; likely description.
Medium | STRY0065263 | Size/Complexity -> priority with no value table. | Add the value table, or drop it (Q8).
Medium | STRY0065263 | I&T Integrations goes to description, but the new HR form has u_it_required. | Map per Q3.
Medium | STRY0065263 | New HR form fields missing: u_functional_area, u_project_category, u_it_required. | Add per the mapping workbook.
Medium | STRY0065263 | No scope rule: Completed (13) and Cancelled (2) would load. | AC: skip Completed and Cancelled.
Medium | STRY0065263 / 65275 | Users are resolved 'via email', but the export holds names only. | Resolve by name (sys_user.name), log no-match rows.
Low | STRY0065263 | Notes -> work_notes; the mapping uses Detailed Description. | Pick one.
High | STRY0065275 | No column says which project a task belongs to, so top_task cannot be set. | Add: Projects column (or parent chain) -> project correlation_id; onBefore sets parent and top_task like 66699.
Low | STRY0065275 | Table name 'planned_task_rel'. | planned_task_rel_planned_task.
Low | STRY0065275 | Milestone by 'name contains Milestone' is a guess. | Confirm with the Asana owner, or drop.
Low | STRY0065275 | Task Status values not listed. | Add the agreed task state table.
Medium | STRY0066715 / 66718 | Coalesce on parent + Title. Titles repeat; reruns can duplicate or merge records. | Coalesce on correlation_id like every other map (confirm issue and risk carry it).
Medium | STRY0066715 | Title says project_issue; AC says issue. On Hold -> Investigating may not be an issue state. | Use one table name; check the issue state choices.
Medium | STRY0067099 | Coalesce on correlation_id on u_lessons_learned, a custom table. | Confirm with the implementation team that the table has correlation_id.
Low | STRY0067099 | Parsing example: input ends in 'Other' but the comment says it returns 'Business Process'. | Fix the example.
Low | STRY0066701 | RAG values (Adaptive colours) to ServiceNow choices not listed. | Add the value table.
Medium | STRY0066721 | Cost plan breakdowns need the fiscal calendar to exist for the budget dates. 'Cost Type + Category' is not unique across periods. | Confirm fiscal periods exist; coalesce on the Adaptive budget line id.
Medium | STRY0066721 | Field names cost_type and resource_type need checking against the instance. | Confirm in the cost_plan dictionary.
High | STRY0066702 | 15 points, three separate builds. Historical time cards and rates create actual-cost records and depend on rate models and fiscal periods. resource_assignment needs confirming as the target table. | Confirm historical time/rates are in scope at all. If yes, split into 3 stories.
Low | STRY0066723 | No points; finding records by correlation_id needs a list view with that column. | Point it; add correlation_id to the list layout. Count files first to size the effort.

## Missing
Id | Story | What it covers
NEW-1 | Mock Load 1 in Dev | Run wave 1 loads in order (Demand, Project, Task). For each entity record: source count, staging rows, inserted, updated, errors. Rerun once: 0 inserts. Spot-check 10 projects against Adaptive/Asana.
NEW-2 | Adaptive task dependencies | Data Source pulls the dependency entity; map to planned_task_rel_planned_task, coalesce on parent + child (both found by correlation_id). Only if dependencies are in scope.
Decision | Value tables | One sheet with every Adaptive and Asana value -> ServiceNow value (state, phase, priority, RAG, funding). Every map story links to it instead of repeating lists.