## How to use
SPM migration field mapping workbook (generated from mapping/*.csv; edit the CSVs, then rebuild)
Start with 'Decisions' (open questions that block the build) and 'Data Quality' (fix in source).
1. Each row maps one source field to one ServiceNow field. 'decision_ref' points to the Decisions sheet.
2. In workshops, set 'status' to Confirmed / Deferred / Not migrating / Open question.
3. 'target_table' shows where the value lands; both pm_project and dmn_demand rows exist
because the same source record can become either, depending on classification.
4. Value Maps holds the state/health/priority translations. target_value must be a stored
value from your instance's sys_choice export, not the display label.
5. 'ServiceNow Form Fields' lists every form field with its (proposed) field name and which source feeds it.
6. Copy agreed changes back into the CSVs (the CSVs are the source of truth for the code).

## Decisions
id | topic | question | options | recommendation | impact_if_undecided | owner | status
D1 | Business Category | The Demand and Project forms use different choice lists for u_business_category (17 vs 11 values; only 2 match exactly, about 6 have a close equivalent; no HR value on projects). Which list wins? | (a) one merged list on both tables (b) keep two lists and map on conversion | (a) One merged list with snake_case stored values incl. Human Resources. Fix before go-live - changing stored values later means a data-fix script | Demand -> project conversion drops or mis-maps the category; HR projects load blank | SN platform owner + PMO | Open
D2 | Asana HR structure | How should the 18 Asana sections (HR COE areas) and the HR tracker land? | (a) Portfolio 'Human Resources' + one program per section (b) portfolio only; section in description (c) section -> department | (a) HR portfolio + programs per section; merge single-item sections (Risk Mitigation; PCC/HR Committee) into a neighbour | Programs referenced by name must exist before load or the field is blank | HR PMO | Open
D3 | Hierarchy | Do Asana tracker subtasks (17 rows) become WBS tasks or sub-projects? Is the Adaptive WBS in scope (the mapping sheet is header-only)? | (a) tasks (b) sub-projects for rows with their own PM/type | (a) Tasks. Only the 3 vendor workstreams under Annual Enrollment have their own PM - keep them as tasks under Annual Enrollment. Adaptive: WBS for Active projects only | Changes load order and volume | HR PMO + Nordic PMO | Open
D4 | Funding | Where do Capex/Opex and the funding pool go? u_funding_type has intake choices (Opex required, Capex required, Accrete Acceleration funds Requested, other) | (a) OOB expense_type for Capex/Opex (b) u_funding_type (c) both | (c) Both: expense_type (OOB, feeds financial reporting) and u_funding_type (keeps intake reports whole). Project Funding Type (19 capital pools) -> u_funding_source; make that a choice list | Split reporting across two fields | Finance + PMO | Open
D5 | Phase | Which phase model? Adaptive: Initiation / Discovery & Design / Execution / Close Out. Asana plans: Project Initiation / Analysis/Design / Build / Test / Communicate / Train / Go-Live / Post Go-Live | (a) one SN phase list + template (b) per-portfolio templates | (b) Two ServiceNow project templates (IT PMO and HR) built from these phases; map Adaptive Phase to pm_project.phase once choices exist | phase passes through as text and is rejected by choice validation | PMO | Open
D6 | Unmapped HR attributes | I&T Integrations Needed, Strategy Focus, Strategy Timeline, HR COEs Engaged, HR Cross-Impacts, Size (projects) have no ServiceNow field | (a) append to description (b) create custom fields (c) drop | (a) Append as a 'Migrated from Asana' block (already built). Create a field only for I&T Integrations if IT wants to report on it | None - default is append | HR PMO | Proposed
D7 | Status mapping | Asana 'Delayed' and 'Started/Scoping' have no ServiceNow state. Asana HR items have no health fields. | (a) Delayed -> Work in Progress + schedule health red (b) Work in Progress only | (a) state 2 + a migration status report with schedule = red | Delayed items look healthy after migration | HR PMO | Proposed
D8 | Business units | Entity/Organization (BSMH, RSFH, GBS, External Partners) and Adaptive Customers -> business_unit. Do these records exist? | (a) create business_unit records (b) use departments | (a) Create BSMH / RSFH / GBS business units; External Partners -> leave blank | Reference fields load blank | SN platform owner | Open
D9 | Demand Type | What u_demand_type do Adaptive demands get? | (a) New Project for all (b) New Application when Business Category = Application | (a) unless Application-category demands follow the application intake path | Demands route to the wrong workflow | Nordic PMO | Open
D10 | Business Owner | Adaptive Business Sponsor is free text (may list several people). Asana HRSP / SME / Project Lead is populated on 10 of 80 rows. u_executive_sponsor has no source. | (a) first resolvable name -> u_business_owner; full text in description (b) leave blank | (a) and ask sponsors to fill u_executive_sponsor after go-live | Mandatory-field validation fails if these become required | PMO | Open
D11 | Cost center | Adaptive 'Dept # for Expense' (cost center table) and Asana Cost Center (blank) have no field on either form | (a) new u_cost_center reference to cmn_cost_center (b) department | (a) if Finance reports by cost center; else (b) | Data lost | Finance | Open
D12 | Nordic lifecycle fields | Next Go-Live Date, Estimate Type, Request Received, Request Assigned, Estimate Complete, Ready For Delivery, Project Assigned have no ServiceNow field | (a) 7 custom fields on pm_project (and the intake ones on dmn_demand) (b) append to description (c) create a linked Completed demand holding intake dates | (a) - these drive leadership and cycle-time reporting. Built into target_mapping as u_ fields | Cycle-time reporting lost | Nordic PMO | Open
D13 | Risk health | Adaptive Risk Health has no OOB project_status indicator | (a) add u_risk_health to project_status (b) drop | (a) - one field; keeps the 6-indicator status view | Risk RAG lost | PMO | Open
D14 | Status history | Migrate only the latest status (Update Notes + health) or the weekly history? | (a) latest only (b) full history | (a) latest only for Adaptive; Asana native status updates (if used) migrate in full | Volume and effort | PMO | Proposed
D15 | Cut-off | Cancelled -> skip; completed > 2 years ago -> skip; completed < 2 years -> header only. Agree? |  | Keep as configured in classification.yaml | Volume | Steering group | Proposed
D16 | Review list | Items routed to review: Asana Not Started with PM = TBD/N/A/blank; tracker rows with no status and no dates; Adaptive Active projects with no Ready For Delivery / Project Assigned date |  | Owners decide via config/overrides.csv | Stay in review and do not load | HR PMO + Nordic PMO | Open

## Data Quality
id | source | issue | evidence | impact | recommended_fix | fix_where | status
DQ1 | Asana | People are names not emails; nicknames differ between fields | PM Assigned: 13 names incl. N/A (9), TBD (3), blank (4). Assignee 'Jennifer ...' vs PM 'Jen ...'; task-level 'Richard' vs tracker 'Rick' | Owners load as the placeholder user | Build data/reference/user_crosswalk.csv from users_referenced.csv (one row per alias). N/A/TBD already treated as blank | Crosswalk file | Open
DQ3 | Asana | Items with no dates | 2 of 80 tracker items have no start or due date; all 17 subtasks under Ireland programs have no dates | ServiceNow requires a start date - falls back to created date | Owners add dates or accept the fallback | Asana (pre-cutover) | Open
DQ4 | Asana | Open items already past due | 27 of the 65 open (not completed or cancelled) tracker items have a due date before 2026-09-22 (oldest 2025-07-31) | Schedule health shows red on day 1; the Gantt view looks wrong | Owners re-baseline or close before the final extract | Asana (pre-cutover) | Open
DQ5 | Asana | Ambiguous Project Type | 'Project/Annual Program' on 4 rows; 4 rows blank | Run vs Change investment class guessed | Owners pick one; default Change | Asana or overrides | Open
DQ6 | Asana | Garbled characters and Asana links in Notes | 7 Notes contain '¬∑¬†' / '‚Äì' (UTF-8 read as Mac Roman); 1 note links to app.asana.com | Unreadable text; dead links after decommission | Auto-repaired by the pipeline (repair_text). Replace Asana links or accept them as legacy pointers | Pipeline (done) | Fixed in code
DQ7 | Asana | Recurring programs copied forward with stale names | Survey rows named '2025' carry 2026 dates | Confusing names in ServiceNow | Rename in Asana before extract | Asana (pre-cutover) | Open
DQ8 | Asana | Sparse attributes | Blank of 80 top-level rows: Strategy Focus 36, Strategy Timeline 34, Entity/Organization 33, HR COEs Engaged 35, HR Cross-Impacts 61, HRSP 70, Funding 78, Cost Center 80, Tags 80 | Low value in ServiceNow | Supports decision D6 (append rather than build fields); drop Cost Center and Tags | Decision | Open
DQ9 | Adaptive | Mapping sheet omits fields ServiceNow needs | No Start Date, Actual Start/End, % Complete, SYSID in the sheet | Projects load with fallback dates | Add them to the extract (already in settings.example.yaml field_map) | Settings (done) | Fixed in config
DQ10 | Adaptive | Pick lists disagree between sheets | State: Projects-sheet dropdown lacks Requested/Draft; Health: 'On Target' (Projects sheet) vs 'On Plan' (Picklists sheet); Estimate Type 'Packaging' only on Picklists sheet; 'Revenue Cycle (includes Ensemble requests' missing ')' | Unmapped values at load | Value maps accept both variants; confirm the live lists via describe-adaptive | Value maps (done) + confirm | Partly fixed
DQ11 | Adaptive | Values not supplied | Region and Customers values are not in the sheet | Sites and business units cannot be fully mapped yet | Export the Region and Customers pick lists | Adaptive export | Open
DQ12 | ServiceNow | Typos in labels and choices | 'GHC - all not FSFH work' (should be non RSFH?); demand Business Category label reads 'Sites'; 'Acrete Acceleration' (Accrete?); 'Demand Mananger'; 'puchases' | User-facing errors | Fix in dev before build freeze | ServiceNow config | Open
DQ13 | ServiceNow | Inconsistent stored choice values | Project list 'urgent care' has a space (others snake_case); demand list mixes 'business intelligence', 'Clinical Monitoring and Dietary', 'lab'; two values share order 200 | Reporting filters and integrations break; changing values after migration needs a data fix | Normalise stored values to snake_case now | ServiceNow config | Open
DQ14 | ServiceNow | Sites list missing markets | Adaptive funding pools include Paducah (PAD) and St Petersburg (STP); neither is on the 25-value Sites list | Region values drop | Add them or confirm Paducah -> Kentucky (value map assumes this) and St Petersburg is retired | ServiceNow config | Open
DQ15 | ServiceNow | Field types disagree between request and form | Request variable 'Executive Sponsor' is Choice; form field u_executive_sponsor is a reference. 'Other Funding Type' text exists on the request but not on the demand/project | Data lost on request -> demand -> project | Align types; add u_other_funding_type if 'other' is used | ServiceNow config | Open
DQ16 | ServiceNow | Notes/Preferences tabs repeat request variables | Project and Demand workbooks list the same 33 catalog variables on Notes and Preferences | Migrated records have no request item - variables cannot be populated | Treat as copy/paste; for any variable leadership reports on (Market President approval, Priority Justification) create a real field | ServiceNow config | Open
DQ17 | Asana | Task-level template quirks | 'Untitled section'; a subtask under a milestone; % Complete stored as 0.5; COE and Entity repeated per task | Odd WBS in ServiceNow | Pipeline: Untitled section -> directly under project; milestones by name; fraction -> percent. COE/Entity per task not migrated | Pipeline (done) | Fixed in code
DQ18 | ServiceNow | Intake category list not supplied | Demand Business Category help says 'same field as Category of project from intake' - the intake 'project category' tab was not provided | Cannot confirm the demand list matches intake | Send the catalog item's Category of Project choices | ServiceNow export | Open

## Asana to ServiceNow
map_id | source_object | source_field | source_type | sample_values | target_table | target_field | target_label | transform_rule | value_map | recommendation | status | decision_ref | notes
AS-P01 | Tracker item (task) | Name | Text |  | pm_project / dmn_demand | short_description | Name | Repair encoding; truncate 160 |  | Map | Proposed
AS-P02 | Tracker item (task) | Section/Column | Section | Benefits & Well-Being; M&A; Compensation; Ireland Projects 2026 - 2027 (18 values) | pm_project / dmn_demand | primary_program | Program | Section name -> pm_program.name | program_name | Map (create 18 HR programs) | Open question | D2 | Sections are HR COE areas. Alternative: department or a COE field. Also appended to description
AS-P03 | Tracker item (task) | Assignee | People | Blank on 79 of 80 rows | [5 empty] | Do not migrate | Proposed |  | PM Assigned is the authoritative owner
AS-P04 | Tracker item (task) | Start Date | Date | 2 rows blank | pm_project / dmn_demand | start_date | Planned start date | Date; fallback created |  | Map | Proposed | DQ3
AS-P05 | Tracker item (task) | Due Date | Date | 27 open rows already past due | pm_project / dmn_demand | end_date / due_date | Planned end date | Date |  | Map | Proposed | DQ4 | Owners should re-baseline past-due In Progress rows before cutover
AS-P06 | Tracker item (task) | Tags | Tags | Blank on all rows | pm_project / dmn_demand | description (append) |  | Append 'Tags:' line |  | Append to description | Proposed
AS-P07 | Tracker item (task) | Notes | Long text | Status-style notes; 7 rows with garbled characters; Asana links | pm_project / dmn_demand | description | Description | Strip HTML; repair encoding |  | Map | Proposed | DQ6 | Notes read like status updates - optionally copy to project_status.comments too
AS-P08 | Tracker item (task) | Parent task | Hierarchy | 17 subtasks under 5 parents | pm_project_task | parent / top_task | Parent | Subtasks become WBS tasks of the tracker item |  | Map | Proposed | D3 | 3 subtasks (vendor workstreams) carry their own PM/type - tasks by default
AS-P09 | Tracker item (task) | Blocked By / Blocking (Dependencies) | Dependencies | Blank on all rows | planned_task_rel_planned_task | parent / child | Predecessor / Successor | Resolve by correlation |  | Map | Proposed
AS-P10 | Tracker item (task) | Project Type | Single select | Project (49); Annual Program (23); Project/Annual Program (4) | pm_project | investment_class | Investment class | Project -> Change; Annual Program -> Run | investment_class | Map | Proposed | DQ5 | Also appended to demand description
AS-P11 | Tracker item (task) | PM Assigned | Text (names) | 13 names incl. N/A (9) and TBD (3); nicknames differ from Assignee | pm_project / dmn_demand | project_manager / assigned_to | Project manager / Demand manager | Name -> sys_user via user_crosswalk.csv; N/A/TBD -> blank |  | Map | Proposed | DQ1 | Build the crosswalk from users_referenced.csv
AS-P12 | Tracker item (task) | Size/Complexity | Single select | Low; Medium; High | dmn_demand / pm_project | size / description (append) | T-Shirt Size | Low->S; Medium->M; High->L | tshirt_size | Map (demand) / Append (project) | Proposed |  | Project form has only calculated scores
AS-P13 | Tracker item (task) | Project Status | Single select | In Progress (44); Completed (13); Not Started (10); Started/Scoping (4); On Hold; Delayed; Cancelled; blank (4) | pm_project / dmn_demand | state | State | Via value map; also drives classification | project_state / demand_state | Map | Proposed | D7 | Delayed -> Work in Progress (+ schedule health red if agreed)
AS-P14 | Tracker item (task) | I&T Integrations Needed | Single select | No Integrations; Yes - New; Yes - Modify Existing; TBD | pm_project / dmn_demand | description (append) |  | Append line |  | Append to description | Open question | D6 | Consider a field if IT wants to report on HR work needing integrations
AS-P15 | Tracker item (task) | HRSP / SME / Project Lead | Text (names) | Populated on 10 of 80 rows | pm_project / dmn_demand | u_business_owner | Business Owner | Name -> sys_user (optional) |  | Map | Open question | D10 | Confirm HRSP = Business Owner
AS-P16 | Tracker item (task) | Strategy Focus | Single select | Be Well Programs; WFI; Workday; M&A... (16 values; 36 blank) | pm_project / dmn_demand | description (append) |  | Append line |  | Append to description | Open question | D6 | Could map to Primary Goal if HR goals are loaded into ServiceNow
AS-P17 | Tracker item (task) | Strategy Timeline | Single select | Long-Term; Annual Changes; Short-Term; One-Time/Non-Interdependent | pm_project / dmn_demand | description (append) |  | Append line |  | Append to description | Proposed | D6
AS-P18 | Tracker item (task) | Funding | Single select | CapEx; OpEx (only 2 rows populated) | pm_project / dmn_demand | expense_type (+ u_funding_type) | Expense type | CapEx->capex; OpEx->opex | expense_type / funding_type | Map | Proposed | D4
AS-P19 | Tracker item (task) | Cost Center | Text | Blank on all rows | pm_project / dmn_demand | u_cost_center | Cost center | Direct |  | Map (if populated) | Proposed | D11
AS-P20 | Tracker item (task) | Entity/Organization | Multi-select | BSMH (39); RSFH (35); GBS; External Partners; 33 blank | pm_project / dmn_demand | business_unit + impacted_business_units | Business Unit / Impacted Business Units | First value -> business_unit; all -> impacted list | business_unit | Map | Proposed | D8
AS-P21 | Tracker item (task) | HR Cross-Impacts | Text | Free text; 61 blank | pm_project / dmn_demand | description (append) |  | Append line |  | Append to description | Proposed | D6
AS-P22 | Tracker item (task) | HR COEs Engaged | Multi-select | Talent & Culture; HRTS; Analytics & Insights... (16 values) | pm_project / dmn_demand | description (append) |  | Append line |  | Append to description | Open question | D6 | Stakeholder register is the ServiceNow-native alternative
AS-P23 | (derived) | n/a | Constant |  | dmn_demand | u_demand_type | Demand Type | All Asana items -> HR | demand_type | Map | Proposed
AS-P24 | (derived) | n/a | Constant |  | dmn_demand | u_business_category | Business Category | All Asana demands -> Human Resources | business_category_demand | Map | Proposed | D1 | Project Business Category list has no HR value
AS-P25 | (derived) | n/a | Constant |  | pm_project / dmn_demand | primary_portfolio / portfolio | Portfolio | All Asana items -> one HR portfolio | portfolio_name | Map | Open question | D2
AS-T01 | Plan task | Task Name | Text | Initiation Milestone 1; Kickoff Meeting | pm_project_task | short_description | Short description | Repair encoding; truncate 160 |  | Map | Proposed
AS-T02 | Plan task | Section | Section | Project Initiation; Analysis/Design; Build; Test; Communicate; Train; Go-Live; Post Go-Live; Untitled section | pm_project_task | parent (phase row) | Phase task | Section -> phase-level task (sections_as_phases); Untitled -> directly under project |  | Map | Proposed |  | Matches a phase-based project template - consider building it in ServiceNow
AS-T03 | Plan task | COE | Single select | Benefits; Compensation; Learning | pm_project_task | description (append) |  | Drop or append |  | Do not migrate | Proposed |  | Project-level COEs already captured
AS-T04 | Plan task | Assigned To | People |  | pm_project_task | assigned_to | Assigned to | Match sys_user email/name |  | Map | Proposed | DQ1
AS-T05 | Plan task | Start Date | Date | Mostly blank | pm_project_task | start_date | Planned start | Date; fallback due date |  | Map | Proposed
AS-T06 | Plan task | Due Date | Date |  | pm_project_task | end_date | Planned end | Date; fallback start date |  | Map | Proposed
AS-T07 | Plan task | Task Status | Single select | In Progress | pm_project_task | state | State | Via value map | task_state | Map | Proposed
AS-T08 | Plan task | % Complete | Percent | 0.5 (fraction in export; '50%' in API) | pm_project_task | percent_complete | % complete | Fraction -> percent |  | Map | Proposed
AS-T09 | Plan task | Tags | Tags |  | pm_project_task |  |  |  |  | Do not migrate | Proposed
AS-T10 | Plan task | Notes | Long text |  | pm_project_task | description | Description | Strip HTML; repair encoding |  | Map | Proposed
AS-T11 | Plan task | Parent task | Hierarchy | Kickoff Meeting under Initiation Milestone 1 | pm_project_task | parent | Parent | Resolve by u_parent_correlation_id |  | Map | Proposed |  | Subtask under a milestone - ServiceNow milestones have zero duration; consider re-parenting to the phase
AS-T12 | Plan task | Blocked By / Blocking | Dependencies |  | planned_task_rel_planned_task | parent / child | Predecessor / Successor | Finish-to-start |  | Map | Proposed
AS-T13 | Plan task | Entity/Organization | Multi-select | RSFH | pm_project_task |  |  |  |  | Do not migrate | Proposed |  | Project-level only in ServiceNow
AS-T14 | Plan task | Collaborators | People | 2 names | pm_project_task | additional_assignee_list | Additional assignee list | Emails -> sys_user list |  | Map | Proposed
AS-T15 | Plan task | (name contains 'Milestone') | Derived | Initiation Milestone 1 | pm_project_task | milestone | Milestone | Name regex 'milestone' (template has no milestone task type) |  | Map | Proposed

## Adaptive to ServiceNow
map_id | source_object | source_field | source_type | sample_values | target_table | target_field | target_label | transform_rule | value_map | recommendation | status | decision_ref | notes
AD-01 | Project | Name | Short text |  | pm_project / dmn_demand | short_description | Name | Truncate 160 |  | Map | Proposed
AD-02 | Project | Project Description | Long text | Scope and business objective | pm_project / dmn_demand | description | Description | Strip HTML; repair encoding |  | Map | Proposed |  | Business Case tab 'In scope' is the alternative home
AD-03 | Project | Manager | User |  | pm_project / dmn_demand | project_manager / assigned_to | Project manager / Demand manager | Email -> sys_user |  | Map | Proposed
AD-04 | Project | Business Sponsor | Free text (multiple names) |  | pm_project / dmn_demand | u_business_owner | Business Owner | First name -> sys_user via crosswalk; full text appended to description if several |  | Map | Open question | D10 | Field help says 'who the PMO works with for scope/funding/approvals' = Business Owner. u_executive_sponsor stays blank unless Adaptive has a separate sponsor
AD-05 | Project | CN# | Number | Capital ID | pm_project / dmn_demand | u_cn | CN | Direct (string - keep leading zeros) |  | Map | Proposed
AD-06 | Project | Dept # for Expense | Pick list (Cost Center table) |  | pm_project / dmn_demand | u_cost_center | Cost center | Match cmn_cost_center by code |  | Map + new field | Open question | D11 | No cost-center field on either form. Alternative: department (if departments carry cost centers)
AD-07 | Project | Region | Multi-select | Location(s) where project will occur | pm_project / dmn_demand | u_sites | Sites | Split; map each to Sites list; script resolves sys_ids | site | Map | Proposed | DQ14 | Region values not in the sheet - export them. Paducah and St Petersburg are not on the Sites list
AD-08 | Project | Next Go-Live Date | Date |  | pm_project | u_next_go_live_date | Next go-live date | Date |  | Map + new field | Open question | D12 | Alternative: a Go-Live milestone task (lost for header-only projects)
AD-09 | Project | Planned Finish | Date | Final go-live date | pm_project / dmn_demand | end_date / due_date | Planned end date | Date |  | Map | Proposed
AD-10 | Project | (Start Date - not in sheet) | Date |  | pm_project / dmn_demand | start_date | Planned start date | Date; fallback Request Received |  | Map | Open question | DQ9 | Required by the ServiceNow schedule engine - add to the Adaptive extract
AD-11 | Project | Project Funding Type | Single select | BSMH IT Capital; CIN (Cincinnati) Capital ... Expense; Clinical Fleet (19 values) | pm_project / dmn_demand | u_funding_source | Funding Source | Direct (label) |  | Map | Proposed | D4 | u_funding_source is a string - consider a choice list with these 19 values
AD-12 | Project | Funding Type | Single select | Opex; Capex | pm_project / dmn_demand | expense_type (+ u_funding_type) | Expense type | Opex->opex; Capex->capex | expense_type / funding_type | Map | Proposed | D4
AD-13 | Project | State | Single select | Requested; Draft; Active; On Hold; Cancelled; Completed | pm_project / dmn_demand | state | State | Via value map; Requested/Draft -> Demand | project_state / demand_state | Map | Proposed | DQ10 | Projects sheet list lacks Requested/Draft - confirm which list is live
AD-14 | Project | Phase | Single select | Initiation; Discovery & Design; Execution; Close Out | pm_project | phase | Phase | Pass through until SN phase choices confirmed | project_phase | Map | Open question | D5 | Phase = Initiation with no delivery dates -> review list
AD-15 | Project | Budget Health | Single select | On Target; Needs Attention; In Trouble | project_status | cost | Cost | Green / Yellow / Red | health | Map (status report) | Proposed
AD-16 | Project | Health | Single select | On Plan; Needs Attention; In Trouble | project_status | overall_health | Overall health | Green / Yellow / Red | health | Map (status report) | Proposed
AD-17 | Project | Resource Health | Single select | On Plan; Needs Attention; In Trouble | project_status | resources | Resources | Green / Yellow / Red | health | Map (status report) | Proposed
AD-18 | Project | Risk Health | Single select | On Plan; Needs Attention; In Trouble | project_status | u_risk_health | Risk health | Green / Yellow / Red | health | Map + new field | Open question | D13 | No OOB risk indicator on status reports - add one or drop
AD-19 | Project | Schedule Health | Single select | On Plan; Needs Attention; In Trouble | project_status | schedule | Schedule | Green / Yellow / Red | health | Map (status report) | Proposed
AD-20 | Project | Scope Health | Single select | On Plan; Needs Attention; In Trouble | project_status | scope | Scope | Green / Yellow / Red | health | Map (status report) | Proposed
AD-21 | Project | Update Notes | Long text | Weekly status notes | project_status | comments | Comments | Latest note -> one status report per project |  | Map (status report) | Proposed | D14 | History only if Adaptive keeps prior notes (Discussions)
AD-22 | Project | Estimate Type | Single select | Detailed Estimate; SAT - Detailed Estimate; Detailed Estimate- Straight to PM; Packaging | pm_project / dmn_demand | u_estimate_type | Estimate type | Via value map | estimate_type | Map + new field | Open question | D12
AD-23 | Project | Request Received | Date |  | pm_project / dmn_demand | u_request_received | Request received | Date |  | Map + new field | Open question | D12 | Lifecycle dates drive Nordic cycle-time reporting
AD-24 | Project | Request Assigned | Date |  | pm_project / dmn_demand | u_request_assigned | Request assigned | Date |  | Map + new field | Open question | D12
AD-25 | Project | Estimate Complete | Date |  | pm_project / dmn_demand | u_estimate_complete | Estimate complete | Date |  | Map + new field | Open question | D12
AD-26 | Project | Ready For Delivery | Date |  | pm_project | u_ready_for_delivery | Ready for delivery | Date; also a classification signal |  | Map + new field | Open question | D12 | Blank on an Active project -> review (still estimating?)
AD-27 | Project | Project Assigned | Date |  | pm_project | u_project_assigned (+ work_start fallback) | Project assigned | Date |  | Map + new field | Open question | D12
AD-28 | Project | Customers | Single select |  | pm_project / dmn_demand | business_unit | Business Unit | Match business_unit.name | business_unit | Map | Proposed | D8 | Values not in the sheet - export them
AD-29 | Project | Business Category | Single select | 11 values (Construction/Relocation ... Urgent Care) | pm_project / dmn_demand | u_business_category | Business Category | Project list: exact stored values. Demand list: about 6 of 11 have a close equivalent | business_category_project / business_category_demand | Map | Open question | D1 | Demand and project choice lists differ - unify before go-live
AD-30 | (derived) | n/a | Constant |  | dmn_demand | u_demand_type | Demand Type | New Project (New Application when category = Application?) | demand_type | Map | Open question | D9
AD-31 | Project | SYSID | System ID | P-00123 | pm_project / dmn_demand | u_legacy_id | Legacy ID | Direct |  | Map + new field | Proposed |  | Plus correlation_id = ADAPTIVE:<entity id> (coalesce key)
AD-32 | Project | % Complete / Actual Start / Actual End | Number / Date |  | pm_project | percent_complete / work_start / work_end | Actuals | Direct |  | Map | Proposed | DQ9 | Not in the sheet but in Adaptive - include in extract
AD-33 | Task / Milestone / Link | WBS | Hierarchy |  | pm_project_task / planned_task_rel_planned_task |  |  | See docs/03 |  | Map (active projects only) | Open question | D3 | Mapping sheet is header-only - confirm whether Adaptive WBS migrates

## ServiceNow Form Fields
form | tab | field_label | custom | field_name | name_source | fed_by_asana | fed_by_adaptive | migration_note
Project | Header | Project Name | No | short_description | Given (form workbook) | Name | Name
Project | Header | Project Manager | No | project_manager | OOB - verify | PM Assigned | Manager
Project | Header | Status | No | status (overall health) | OOB - verify |  | Health | Confirm what 'Status' is on your form; health is best loaded via project_status
Project | Header | State | No | state | OOB - verify | Project Status | State | Integers in sys_choice
Project | Header | Percent Complete |  | percent_complete | OOB - verify | (rolled up from tasks) | % Complete | Rolls up once tasks exist
Project | Header | Number | No | number | OOB - verify |  |  | Auto-numbered; source ID goes to u_legacy_id
Project | Header | Assigned To | No | assigned_to | OOB - verify
Project | Header | Assignment Group | No | assignment_group | OOB - verify |  |  | Not fed by either source
Project | Header | Additional assignee list | No | additional_assignee_list | OOB - verify
Project | Header | Detailed Description | No | description | OOB - verify | Notes | Project Description
Project | Dates | Schedule |  | schedule | OOB - verify |  |  | Calendar reference - set a default
Project | Dates | Approved start date |  | approved_start_date | OOB - verify |  |  | No source; leave blank
Project | Dates | Planned start date |  | start_date | OOB - verify | Start Date | (StartDate - add to extract) | Required
Project | Dates | Actual start date |  | work_start | OOB - verify |  | Actual start / Project Assigned
Project | Dates | Duration |  | duration | Calculated - do not load |  |  | Derived from dates
Project | Dates | Planned effort |  | effort | OOB - verify |  | Work (hours) | Only if resource planning is in scope
Project | Dates | Approved end date |  | approved_end_date | OOB - verify |  |  | No source; leave blank
Project | Dates | Planned end date |  | end_date | OOB - verify | Due Date | Planned Finish
Project | Dates | Actual end date |  | work_end | OOB - verify | completed_at | Actual end
Project | Dates | Actual duration |  | work_duration | Calculated - do not load
Project | Dates | Actual effort |  | work_effort | Calculated - do not load |  |  | Rolls up from time cards
Project | Details | Portfolio | No | primary_portfolio | OOB - verify | (constant: HR portfolio)
Project | Details | Program | No | primary_program | OOB - verify | Section/Column |  | Create the programs before loading
Project | Details | Business Owner | Yes | u_business_owner | Given (form workbook) | HRSP / SME / Project Lead | Business Sponsor | Reference sys_user
Project | Details | Executive Sponsor | Yes | u_executive_sponsor | Given (form workbook) |  |  | No reliable source in either system
Project | Details | Investment Class | No | investment_class | OOB - verify | Project Type | (default Change) | Run vs Change
Project | Details | Investment Type | No | investment_type | OOB - verify
Project | Details | Execution Type | No | execution_type | OOB - verify |  |  | Default waterfall
Project | Details | Expense type | No | expense_type | OOB - verify | Funding | Funding Type
Project | Details | CN | Yes | u_cn | Given (form workbook) |  | CN#
Project | Details | Funding Type | Yes | u_funding_type | Given (form workbook) | Funding | Funding Type | Choice list is intake-oriented (Opex required ...) - see decision D4
Project | Details | Funding Source | Yes | u_funding_source | Given (form workbook) |  | Project Funding Type
Project | Details | Priority | No | priority | OOB - verify |  |  | No source in either system
Project | Details | Phase | No | phase | OOB - verify | (plan-project sections become phase tasks) | Phase
Project | Details | Business Category | Yes | u_business_category | Given (form workbook) | (no HR value in the project list) | Business Category | Project list differs from demand list - decision D1
Project | Details | Department | No | department | OOB - verify |  | Dept # for Expense? | Or u_cost_center - decision D11
Project | Details | Business Unit | No | business_unit | OOB - verify | Entity/Organization (first) | Customers
Project | Details | Sites | Yes | u_sites | Given (form workbook) |  | Region | List - transform script resolves names to sys_ids
Project | Details | Impacted Business Units | No | impacted_business_units | OOB - verify | Entity/Organization
Project | Details | Business Capabilities | No | business_capabilities | OOB - verify
Project | Details | Impacted Business Applications | No | business_applications | OOB - verify
Project | Business Case | Strategic Priority | No | strategic_priority | OOB - verify
Project | Business Case | Primary Goal | No | primary_goal | OOB - verify | Strategy Focus? |  | Only if HR goals are loaded
Project | Business Case | Business Case | No | business_case | OOB - verify
Project | Business Case | Risk of Performing / not Performing | No | risk_of_performing / risk_of_not_performing | OOB - verify
Project | Business Case | Enablers / Barriers | No | enablers / barriers | OOB - verify
Project | Business Case | In scope / Out of scope / Assumptions | No | in_scope / out_of_scope / assumptions | OOB - verify |  | Project Description (scope)
Project | Financials | All financial fields | No | (cost_plan / benefit_plan roll-ups) | Calculated - do not load |  |  | Neither source supplies budget amounts
Project | Score | Risk / Value / Size Score, Score | No | risk_score / value_score / size_score / score | Calculated - do not load |  |  | Calculated from assessments
Project | Notes / Preferences | Request variables (Requested For ... Priority Justification) |  | (catalog variables) | Not loadable |  |  | These tabs repeat the request variables. Migrated records have no request, so variables cannot be populated (DQ16)
Demand | Header | Name | No | short_description | OOB - verify | Name | Name
Demand | Header | Category | No | category | OOB - verify |  |  | strategic/operational default
Demand | Header | Type | No | type | OOB - verify |  |  | Constant project; drives 'Convert to'
Demand | Header | Demand Type | Yes | u_demand_type | Given (form workbook) | (constant HR) | (constant New Project)
Demand | Header | Number | No | number | OOB - verify
Demand | Header | Approved start / end date | No | approved_start_date / approved_end_date | OOB - verify
Demand | Header | Planned start date | No | start_date | OOB - verify | Start Date | StartDate
Demand | Header | Planned end date | No | due_date | OOB - verify | Due Date | Planned Finish | Confirm: demand uses due_date
Demand | Header | Detailed Description | No | description | OOB - verify | Notes | Project Description
Demand | Details | Portfolio / Program | No | portfolio / primary_program | OOB - verify | (HR portfolio) / Section
Demand | Details | Business Owner | Yes | u_business_owner | Given (form workbook) | HRSP / SME / Project Lead | Business Sponsor
Demand | Details | Executive Sponsor | Yes | u_executive_sponsor | Given (form workbook)
Demand | Details | Investment Class / Type | No | investment_class / investment_type | OOB - verify | Project Type
Demand | Details | Expense type | No | expense_type | OOB - verify | Funding | Funding Type
Demand | Details | CN | Yes | u_cn | Given (form workbook) |  | CN#
Demand | Details | Funding Type | Yes | u_funding_type | Given (form workbook) | Funding | Funding Type
Demand | Details | Funding Source | Yes | u_funding_source | Given (form workbook) |  | Project Funding Type
Demand | Details | Priority | No | priority | OOB - verify
Demand | Details | Business Category | Yes | u_business_category | Given (form workbook) | (Human Resources) | Business Category | Label shows 'Sites' in the workbook (typo, DQ12)
Demand | Details | Department / Business Unit | No | department / business_unit | OOB - verify | Entity/Organization | Customers
Demand | Details | Sites | Yes | u_sites | Given (form workbook) |  | Region
Demand | Details | Demand Manager | No | assigned_to (or demand_manager) | OOB - verify | PM Assigned | Manager
Demand | Details | Project Manager | No | project_manager | OOB - verify | PM Assigned | Manager | Carried to the project on conversion
Demand | Details | Impacted Business Units / Capabilities / Applications | No | impacted_business_units / business_capabilities / business_applications | OOB - verify | Entity/Organization
Demand | Business Case | (same fields as the project form) | No | business_case, in_scope, ... | OOB - verify
Demand | Financials | All financial fields | No | (calculated) | Calculated - do not load
Demand | Assessment Data | Impact / Risk / Value / T-Shirt Size / Score / Assessment Required | No | impact / risk / value / size / score / assessment_required | OOB - verify | Size/Complexity -> size |  | Scores are calculated from assessments
Demand | Notes / Preferences / RequesT | Request variables |  | (catalog variables) | Not loadable |  |  | Same as the project form (DQ16)

## Value Maps
map_name | source_system | source_value | target_value | notes
demand_type | * | asana | hr | u_demand_type: all Asana items are HR work. CONFIRM stored value (form lists labels New Application / New Project / HR)
demand_type | * | adaptive | new_project | Adaptive/Nordic IT work. Use new_application for Business Category = Application if agreed (decision D9). CONFIRM stored value
demand_state | asana | open | submitted | Intake task still open. Confirm stored value in sys_choice (dmn_demand.state)
demand_state | asana | Not Started | qualified | HR tracker item not started (only reaches demand via review/override)
demand_state | asana | Started/Scoping | screening
demand_state | asana | On Hold | deferred
demand_state | asana | Cancelled | incomplete
demand_state | asana | active | draft | Pipeline-portfolio project not yet approved
demand_state | asana | completed | completed
demand_state | adaptive | Requested | submitted | Nordic request received / being estimated
demand_state | adaptive | Draft | draft
demand_state | adaptive | Active | screening | Active but not yet Ready For Delivery (estimation in progress) - via review/override
demand_state | adaptive | On Hold | deferred
demand_state | adaptive | Cancelled | incomplete
demand_state | * |  | draft | Blank source value
demand_category | * |  | strategic | OOB category. Values: strategic ¦ operational (confirm in sys_choice)
project_state | asana | Not Started | -5 | Pending (OOB pm_project.state integers - CONFIRM in sys_choice)
project_state | asana | Started/Scoping | 1 | Open
project_state | asana | In Progress | 2 | Work in Progress
project_state | asana | Delayed | 2 | Work in Progress + schedule health red on status report (decision D7)
project_state | asana | On Hold | -3 | On Hold - CONFIRM value exists in your release
project_state | asana | Completed | 3 | Closed Complete
project_state | asana | Cancelled | 4 | Closed Incomplete (only if cancelled work is migrated; default rule skips it)
project_state | asana | active | 2 | Standard Asana project (derived status)
project_state | asana | on_hold | -3
project_state | asana | completed | 3
project_state | asana | archived | 3
project_state | asana | open | -5 | Tracker item with no Project Status
project_state | adaptive | Requested | -5 | Normally classified as demand
project_state | adaptive | Draft | -5 | Normally classified as demand
project_state | adaptive | Active | 2 | Work in Progress
project_state | adaptive | On Hold | -3 | On Hold - CONFIRM
project_state | adaptive | Completed | 3 | Closed Complete
project_state | adaptive | Cancelled | 4 | Closed Incomplete
task_state | asana | Not Started | -5 | Task Status custom field (task-level template)
task_state | asana | In Progress | 2
task_state | asana | Completed | 3
task_state | asana | On Hold | -3 | CONFIRM
task_state | asana | not_started | -5 | Derived when Task Status is blank
task_state | asana | in_progress | 2
task_state | asana | completed | 3
task_state | adaptive | Draft | -5
task_state | adaptive | Active | 2
task_state | adaptive | On Hold | -3 | CONFIRM
task_state | adaptive | Completed | 3
task_state | adaptive | Cancelled | 7 | Closed Skipped
task_state | * |  | -5 | Blank -> Pending (e.g. phase rows)
health | adaptive | On Target | green | Budget Health list uses On Target
health | adaptive | On Plan | green | Health/Resource/Risk/Schedule/Scope lists use On Plan (picklist sheet) - same meaning
health | adaptive | Needs Attention | yellow
health | adaptive | In Trouble | red
health | asana | on_track | green | Asana native status updates
health | asana | at_risk | yellow
health | asana | off_track | red
health | asana | on_hold | yellow
health | asana | complete | green
investment_class | asana | Project | change | OOB investment_class (Run vs Change). CONFIRM stored values
investment_class | asana | Annual Program | run | Recurring annual programs are Run work
investment_class | asana | Project/Annual Program | change | Ambiguous - defaulted to Change; owners to confirm (data-quality DQ5)
investment_class | * |  | change | Default (all Adaptive/Nordic work is project delivery)
expense_type | * | Capex | capex | OOB expense type. CONFIRM stored values
expense_type | * | Opex | opex
funding_type | * | Capex | capex_required | u_funding_type choice 'Capex required'. CONFIRM stored value (decision D4)
funding_type | * | Opex | opex_required | u_funding_type choice 'Opex required'. CONFIRM stored value
business_category_project | adaptive | Construction/Relocation | construction_relocation | Stored values from Project_Form_Fields 'Business category' tab
business_category_project | adaptive | Onboarding (new Provider group - no construction) | onboarding
business_category_project | adaptive | Application | application
business_category_project | adaptive | Epic | epic
business_category_project | adaptive | GHC - all non RSFH work | ghc | SN label reads 'GHC - all not FSFH work' (typo - DQ12)
business_category_project | adaptive | Infrastructure | infrastructure
business_category_project | adaptive | Medical Group | medical_group
business_category_project | adaptive | Revenue Cycle (includes Ensemble requests | revenue_cycle | Source value is missing its closing parenthesis
business_category_project | adaptive | Revenue Cycle (includes Ensemble requests) | revenue_cycle
business_category_project | adaptive | RSFH | rsfh
business_category_project | adaptive | Security | security
business_category_project | adaptive | Urgent Care | urgent care | SN stored value contains a space - fix before go-live (DQ13)
business_category_demand | asana |  | Human Resources | All Asana (HR) demands. Demand list stored values from Demand_Form_Fields
business_category_demand | adaptive | Construction/Relocation | Construction Renovation Relocation | Demand list differs from project list (decision D1)
business_category_demand | adaptive | Onboarding (new Provider group - no construction) | Employed Physician Onboarding | Closest match - CONFIRM
business_category_demand | adaptive | Epic | EHR
business_category_demand | adaptive | Infrastructure | Infrastructure
business_category_demand | adaptive | Revenue Cycle (includes Ensemble requests | Rev Cycle
business_category_demand | adaptive | Revenue Cycle (includes Ensemble requests) | Rev Cycle
business_category_demand | adaptive | Security | Security
site | * | Cincinnati | Cincinnati | u_sites list; transform script resolves names to sys_ids. Region values not supplied - extend once exported
site | * | CIN | Cincinnati | Market codes used in Project Funding Type
site | * | Greenville | Greenville
site | * | GVL | Greenville
site | * | Hampton Roads | Hampton Roads
site | * | HMP | Hampton Roads
site | * | Lima | Lima
site | * | LIM | Lima
site | * | Lorain | Lorain
site | * | LOR | Lorain
site | * | Richmond | Richmond
site | * | RCH | Richmond
site | * | Springfield | Springfield
site | * | SPG | Springfield
site | * | Toledo | Toledo
site | * | TOL | Toledo
site | * | Youngstown | Youngstown
site | * | YNG | Youngstown
site | * | Home Office | Home Office
site | * | RSFH | Roper St. Francis Healthcare
site | * | Roper St Francis | Roper St. Francis Healthcare
site | * | Ireland | Ireland
site | * | Enterprise | Enterprise
site | * | Paducah | Kentucky | ASSUMPTION - Paducah is not on the Sites list (DQ14). CONFIRM
site | * | PAD | Kentucky | ASSUMPTION - CONFIRM
business_unit | * | BSMH | BSMH | Entity/Organization + Customers -> business_unit (name must match business_unit.name). CONFIRM names
business_unit | * | RSFH | RSFH
business_unit | * | GBS | GBS
business_unit | * | External Partners | External Partners | May not warrant a business unit - decision D8
tshirt_size | * | Low | small | Size/Complexity -> demand T-Shirt Size. CONFIRM stored values
tshirt_size | * | Medium | medium
tshirt_size | * | High | large
estimate_type | adaptive | Detailed Estimate | detailed_estimate | Proposed new choice field u_estimate_type (we define the values)
estimate_type | adaptive | SAT - Detailed Estimate | sat_detailed_estimate
estimate_type | adaptive | Detailed Estimate- Straight to PM | detailed_estimate_straight_to_pm
estimate_type | adaptive | Packaging | packaging | Only on the Picklists sheet - confirm it is in use
program_name | asana | Ireland Projects 2026 - 2027 | Ireland Projects 2026 - 2027 | Asana sections -> pm_program.name (decision D2). Other sections pass through unchanged
portfolio_name | asana |  | Human Resources | ASSUMPTION: every Asana item belongs to one HR portfolio (decision D2)
priority | * | Critical | 1 | 1 - Critical (task.priority) - neither source has priority today
priority | * | High | 2
priority | * | Medium | 3
priority | * | Low | 4
dependency_type | * | fs | fs | Finish to Start
dependency_type | adaptive | Finish to Start | fs
dependency_type | adaptive | Start to Start | ss
dependency_type | adaptive | Finish to Finish | ff
dependency_type | adaptive | Start to Finish | sf
project_phase | * |  |  | Adaptive Phase passes through; map once SN phase choices are confirmed (decision D5)