## Stories
Number | Wave | Short description | Points | Acceptance criteria | Acceptance criteria (HTML - paste into ServiceNow)
NEW-10 | A - now | API Discovery: confirm Adaptive entities/fields and Asana content | 2 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Purpose: the related-record Data Sources need exact Adaptive entity and field names. One script prints them, so nothing is guessed. - Run servicenow/discovery_background_script.js in Scripts - Background (Dev), after at least one Adaptive project is loaded. - Download the output and attach it to this story. - From the output, record on this story: the entity names for tasks, milestones, issues, risks, lessons learned, resource links, timesheets and attachments; and the field on each that points at the project (usually Project; lessons: C_RelatedWorkItem). - From the Asana section, record: whether portfolio items have subtasks, attachments, and actual_time_minutes (time tracking). - Done when every [CONFIRM] value in STRY0067506, NEW-13 and STRY0066723 is filled in. | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Purpose: the related-record Data Sources need exact Adaptive entity and field names. One script prints them, so nothing is guessed.</p> <ul style="list-style-position: inside;"><li>Run servicenow/discovery_background_script.js in Scripts - Background (Dev), after at least one Adaptive project is loaded.</li><li>Download the output and attach it to this story.</li><li>From the output, record on this story: the entity names for tasks, milestones, issues, risks, lessons learned, resource links, timesheets and attachments; and the field on each that points at the project (usually Project; lessons: C_RelatedWorkItem).</li><li>From the Asana section, record: whether portfolio items have subtasks, attachments, and actual_time_minutes (time tracking).</li><li>Done when every [CONFIRM] value in STRY0067506, NEW-13 and STRY0066723 is filled in.</li></ul>
STRY0067504 | A - now | Create Outbound REST Message for AdaptiveWork (Clarizen) API | 1 | Status: connection proven in Dev (POST /data/query and GET /metadata/describeEntities return 200). This story is complete when: - Base URL is the system property x_mig.adaptive.url = https://api2.clarizen.com/v2.0/services; key in x_mig.adaptive.key (type password2). Asana: x_mig.asana.token (password2), x_mig.asana.project_gid = HR Project Portfolio 2026. - The keys are switched to the svc_sn_migration service account keys (Adaptive and Asana) once issued; only the property values change. - The same four properties exist in Test and Prod (values are entered per instance; they do not move with code). - Field metadata is read with GET (not POST) /metadata/describeEntities?typeNames=<Entity>. | <p>Status: connection proven in Dev (POST /data/query and GET /metadata/describeEntities return 200).</p> <p>This story is complete when:</p> <ul style="list-style-position: inside;"><li>Base URL is the system property x_mig.adaptive.url = https://api2.clarizen.com/v2.0/services; key in x_mig.adaptive.key (type password2). Asana: x_mig.asana.token (password2), x_mig.asana.project_gid = HR Project Portfolio 2026.</li><li>The keys are switched to the svc_sn_migration service account keys (Adaptive and Asana) once issued; only the property values change.</li><li>The same four properties exist in Test and Prod (values are entered per instance; they do not move with code).</li><li>Field metadata is read with GET (not POST) /metadata/describeEntities?typeNames=&lt;Entity&gt;.</li></ul>
STRY0067506 | B | Create API Data Sources for Adaptive related records | 8 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Each staging table gets three String(100) columns if missing: Correlation ID, Parent Correlation ID, Project Correlation ID (same way Correlation ID was added to u_import_adaptive_projects). Pattern: copy servicenow/adaptive_related_data_source.js into a new Data Source (Type: Custom (Load by Script)) and change only its CONFIG block. It loads records ONLY for projects already in pm_project with an ADAPTIVE: correlation_id, 20 projects per query, following paging. Data Source ¦ Staging table ¦ ENTITY ¦ PROJECT_FIELD ¦ Notes Adaptive Tasks - API ¦ u_import_adaptive_project_tasks ¦ Task ¦ Project ¦ Parent Correlation ID = @Parent, Project Correlation ID = @Project, Milestone = '=false' Adaptive Milestones - API ¦ u_import_adaptive_project_tasks ¦ Milestone ¦ Project ¦ Same MAP; Milestone = '=true' Adaptive Risks - API ¦ u_import_adaptive_risks ¦ Risk [CONFIRM] ¦ [CONFIRM] ¦ MAP labels = the staging table's column labels Adaptive Issues - API ¦ u_import_adaptive_issues ¦ Issue [CONFIRM] ¦ [CONFIRM] ¦ MAP labels = the staging table's column labels Adaptive Lessons - API ¦ u_import_adaptive_lessons (new) ¦ C_PMOLessonsLearned ¦ C_RelatedWorkItem ¦ Preset in the script comments Adaptive Resources - API ¦ u_import_adaptive_resources (new) ¦ [CONFIRM] e.g. RegularResourceLink ¦ [CONFIRM] ¦ Columns: Correlation ID, Project Correlation ID (the work item), Resource Email, Units/Hours Adaptive Time - API ¦ u_import_adaptive_time (new) ¦ [CONFIRM] e.g. Timesheet ¦ Project ¦ Columns: Correlation ID, Project Correlation ID (@WorkItem), Reported By Email, Reported Date, Duration This story is complete when: - Each Data Source above exists, and 'Load All Records' completes with no errors in the import log. - The import log line 'rows loaded: N (for M projects)' matches a count in Adaptive for the pilot projects. - Every staging row has Correlation ID and Project Correlation ID filled; task rows also Parent Correlation ID. - Reference values arrive as plain text (e.g. 'Active', not {"id":"/State/Active"}); dates as yyyy-MM-dd. - Data Sources are not scheduled; they are run by hand in Run order (see Run order tab). | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Each staging table gets three String(100) columns if missing: Correlation ID, Parent Correlation ID, Project Correlation ID (same way Correlation ID was added to u_import_adaptive_projects).</p> <p>Pattern: copy servicenow/adaptive_related_data_source.js into a new Data Source (Type: Custom (Load by Script)) and change only its CONFIG block. It loads records ONLY for projects already in pm_project with an ADAPTIVE: correlation_id, 20 projects per query, following paging.</p> <table style="width: 100%;"><thead><tr><td><strong>Data Source</strong></td><td><strong>Staging table</strong></td><td><strong>ENTITY</strong></td><td><strong>PROJECT_FIELD</strong></td><td><strong>Notes</strong></td></tr></thead><tbody><tr><td>Adaptive Tasks - API</td><td>u_import_adaptive_project_tasks</td><td>Task</td><td>Project</td><td>Parent Correlation ID = @Parent, Project Correlation ID = @Project, Milestone = &#x27;=false&#x27;</td></tr><tr><td>Adaptive Milestones - API</td><td>u_import_adaptive_project_tasks</td><td>Milestone</td><td>Project</td><td>Same MAP; Milestone = &#x27;=true&#x27;</td></tr><tr><td>Adaptive Risks - API</td><td>u_import_adaptive_risks</td><td>Risk [CONFIRM]</td><td>[CONFIRM]</td><td>MAP labels = the staging table&#x27;s column labels</td></tr><tr><td>Adaptive Issues - API</td><td>u_import_adaptive_issues</td><td>Issue [CONFIRM]</td><td>[CONFIRM]</td><td>MAP labels = the staging table&#x27;s column labels</td></tr><tr><td>Adaptive Lessons - API</td><td>u_import_adaptive_lessons (new)</td><td>C_PMOLessonsLearned</td><td>C_RelatedWorkItem</td><td>Preset in the script comments</td></tr><tr><td>Adaptive Resources - API</td><td>u_import_adaptive_resources (new)</td><td>[CONFIRM] e.g. RegularResourceLink</td><td>[CONFIRM]</td><td>Columns: Correlation ID, Project Correlation ID (the work item), Resource Email, Units/Hours</td></tr><tr><td>Adaptive Time - API</td><td>u_import_adaptive_time (new)</td><td>[CONFIRM] e.g. Timesheet</td><td>Project</td><td>Columns: Correlation ID, Project Correlation ID (@WorkItem), Reported By Email, Reported Date, Duration</td></tr></tbody></table> <p>This story is complete when:</p> <ul style="list-style-position: inside;"><li>Each Data Source above exists, and &#x27;Load All Records&#x27; completes with no errors in the import log.</li><li>The import log line &#x27;rows loaded: N (for M projects)&#x27; matches a count in Adaptive for the pilot projects.</li><li>Every staging row has Correlation ID and Project Correlation ID filled; task rows also Parent Correlation ID.</li><li>Reference values arrive as plain text (e.g. &#x27;Active&#x27;, not {&quot;id&quot;:&quot;/State/Active&quot;}); dates as yyyy-MM-dd.</li><li>Data Sources are not scheduled; they are run by hand in Run order (see Run order tab).</li></ul>
NEW-11 | B | Create API Data Sources for Asana HR portfolio (projects and work plans) | 5 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Replaces the CSV loads for u_import_asana_hr_project_portfolio and u_import_asana_project_tasks. The existing transform maps stay; the script fills the same columns (matched by label), and fills any other column whose label equals an Asana custom field name (Project Status, PM Assigned, Funding, Entity/Organization, ...). - Add String(100) columns: Correlation ID (both tables); Parent Correlation ID and Project Correlation ID (tasks table); optional Assignee Email and Completed. - Data Source 'Asana Portfolio - API' -> u_import_asana_hr_project_portfolio, script servicenow/asana_data_source.js with MODE = 'projects'. - Data Source 'Asana Work Plan - API' -> u_import_asana_project_tasks, same script with MODE = 'tasks' (walks subtasks at every level). - PILOT list holds the pilot item names; [] loads every item. Items with Project Status Completed or Cancelled are skipped (agreed in-flight rule). - Both transform maps get a field map u_correlation_id -> correlation_id with Coalesce = true. - People: transform maps match sys_user on email (Assignee Email column) and fall back to name. - Done when the pilot items and their subtasks load, transform, and a second run gives 0 inserts. | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Replaces the CSV loads for u_import_asana_hr_project_portfolio and u_import_asana_project_tasks. The existing transform maps stay; the script fills the same columns (matched by label), and fills any other column whose label equals an Asana custom field name (Project Status, PM Assigned, Funding, Entity/Organization, ...).</p> <ul style="list-style-position: inside;"><li>Add String(100) columns: Correlation ID (both tables); Parent Correlation ID and Project Correlation ID (tasks table); optional Assignee Email and Completed.</li><li>Data Source &#x27;Asana Portfolio - API&#x27; -&gt; u_import_asana_hr_project_portfolio, script servicenow/asana_data_source.js with MODE = &#x27;projects&#x27;.</li><li>Data Source &#x27;Asana Work Plan - API&#x27; -&gt; u_import_asana_project_tasks, same script with MODE = &#x27;tasks&#x27; (walks subtasks at every level).</li><li>PILOT list holds the pilot item names; [] loads every item. Items with Project Status Completed or Cancelled are skipped (agreed in-flight rule).</li><li>Both transform maps get a field map u_correlation_id -&gt; correlation_id with Coalesce = true.</li><li>People: transform maps match sys_user on email (Assignee Email column) and fall back to name.</li><li>Done when the pilot items and their subtasks load, transform, and a second run gives 0 inserts.</li></ul>
NEW-12 | C | Work plans: load Adaptive and Asana tasks into pm_project_task | 5 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Uses the existing maps 'Import Adaptive Project Tasks Transform Map' and 'Import Asana Project Tasks Transform Map'. Feeds: STRY0067506 (Tasks + Milestones) and NEW-11 (Work Plan). - Field map u_correlation_id -> correlation_id, Coalesce = true (both maps). - onBefore script (below) sets parent and top_task from the staging columns; a row whose project is missing is skipped with a log message. - Run business rules = on, so dates and percent complete roll up to the project. - Children can arrive before parents: run the transform twice. The second run attaches the rest (coalesce makes it an update). - Field maps per the value tables below. Task state values for Adaptive are PROPOSED (decision D1). - After the load, open each pilot project's Project Tasks list: the hierarchy matches Adaptive/Asana and the project's dates are re-checked against the source (ServiceNow recalculates project dates from tasks). (function runTransformScript(source, map, log, target) { function find(table, corr) { var g = new GlideRecord(table); return (corr && g.get('correlation_id', corr)) ? g.getUniqueValue() : ''; } var project = find('pm_project', source.u_project_correlation_id + ''); if (!project) { log.warn('No project for ' + source.u_correlation_id); ignore = true; return; } var parentCorr = source.u_parent_correlation_id + ''; var parent = (parentCorr == source.u_project_correlation_id + '') ? project : find('planned_task', parentCorr); target.top_task = project; target.parent = parent ¦¦ project; // parent not loaded yet: second run fixes it })(source, map, log, target); Source ¦ Source value ¦ pm_project_task Adaptive Name / Asana name ¦ ¦ short_description StartDate / start_on ¦ ¦ start_date DueDate / due_on ¦ ¦ end_date PercentCompleted ¦ ¦ percent_complete Milestone column ¦ true ¦ milestone = true Adaptive State (PROPOSED, D1) ¦ Draft, Requested, On Hold ¦ Pending ¦ Active ¦ Work in Progress ¦ Completed ¦ Closed Complete ¦ Cancelled ¦ Closed Incomplete Asana Task Status (agreed) ¦ Not Started, On Hold, blank ¦ Pending ¦ Started/Scoping ¦ Investigating ¦ In Progress, Delayed ¦ Work in Progress ¦ Completed (or completed = true) ¦ Closed Complete ¦ Cancelled ¦ Closed Incomplete Asana Notes ¦ ¦ work_notes Asana Collaborators ¦ names ¦ additional_assignee_list (sys_user by name) | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Uses the existing maps &#x27;Import Adaptive Project Tasks Transform Map&#x27; and &#x27;Import Asana Project Tasks Transform Map&#x27;. Feeds: STRY0067506 (Tasks + Milestones) and NEW-11 (Work Plan).</p> <ul style="list-style-position: inside;"><li>Field map u_correlation_id -&gt; correlation_id, Coalesce = true (both maps).</li><li>onBefore script (below) sets parent and top_task from the staging columns; a row whose project is missing is skipped with a log message.</li><li>Run business rules = on, so dates and percent complete roll up to the project.</li><li>Children can arrive before parents: run the transform twice. The second run attaches the rest (coalesce makes it an update).</li><li>Field maps per the value tables below. Task state values for Adaptive are PROPOSED (decision D1).</li><li>After the load, open each pilot project&#x27;s Project Tasks list: the hierarchy matches Adaptive/Asana and the project&#x27;s dates are re-checked against the source (ServiceNow recalculates project dates from tasks).</li></ul> <pre><code>(function runTransformScript(source, map, log, target) { function find(table, corr) { var g = new GlideRecord(table); return (corr &amp;&amp; g.get(&#x27;correlation_id&#x27;, corr)) ? g.getUniqueValue() : &#x27;&#x27;; } var project = find(&#x27;pm_project&#x27;, source.u_project_correlation_id + &#x27;&#x27;); if (!project) { log.warn(&#x27;No project for &#x27; + source.u_correlation_id); ignore = true; return; } var parentCorr = source.u_parent_correlation_id + &#x27;&#x27;; var parent = (parentCorr == source.u_project_correlation_id + &#x27;&#x27;) ? project : find(&#x27;planned_task&#x27;, parentCorr); target.top_task = project; target.parent = parent ¦¦ project; // parent not loaded yet: second run fixes it })(source, map, log, target);</code></pre> <table style="width: 100%;"><thead><tr><td><strong>Source</strong></td><td><strong>Source value</strong></td><td><strong>pm_project_task</strong></td></tr></thead><tbody><tr><td>Adaptive Name / Asana name</td><td></td><td>short_description</td></tr><tr><td>StartDate / start_on</td><td></td><td>start_date</td></tr><tr><td>DueDate / due_on</td><td></td><td>end_date</td></tr><tr><td>PercentCompleted</td><td></td><td>percent_complete</td></tr><tr><td>Milestone column</td><td>true</td><td>milestone = true</td></tr><tr><td>Adaptive State (PROPOSED, D1)</td><td>Draft, Requested, On Hold</td><td>Pending</td></tr><tr><td></td><td>Active</td><td>Work in Progress</td></tr><tr><td></td><td>Completed</td><td>Closed Complete</td></tr><tr><td></td><td>Cancelled</td><td>Closed Incomplete</td></tr><tr><td>Asana Task Status (agreed)</td><td>Not Started, On Hold, blank</td><td>Pending</td></tr><tr><td></td><td>Started/Scoping</td><td>Investigating</td></tr><tr><td></td><td>In Progress, Delayed</td><td>Work in Progress</td></tr><tr><td></td><td>Completed (or completed = true)</td><td>Closed Complete</td></tr><tr><td></td><td>Cancelled</td><td>Closed Incomplete</td></tr><tr><td>Asana Notes</td><td></td><td>work_notes</td></tr><tr><td>Asana Collaborators</td><td>names</td><td>additional_assignee_list (sys_user by name)</td></tr></tbody></table>
STRY0066701 | C | Status reports: Adaptive project health -> project_status | 3 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Adaptive keeps health on the project itself (Health, Schedule/Budget/Resource/Scope/Risk Health, Update Notes), so no extra API call is needed: a SECOND transform map on the same staging table u_import_adaptive_projects creates one status report per project. Asana: no status reports for HR portfolio items (they are tasks); not in scope. - System property x_mig.status_as_on (string, yyyy-MM-dd) = the migration date, e.g. 2026-10-30. Fixed date = reruns update instead of adding reports. - New transform map 'Import Adaptive Status Reports' : u_import_adaptive_projects -> project_status, Order 200 (runs after the project map, Order 100). - Field map 1: [Script] -> project, Coalesce = true: answer = sys_id of pm_project whose correlation_id = source.u_correlation_id. - Field map 2: [Script] -> as_on, Coalesce = true: answer = gs.getProperty('x_mig.status_as_on'). - onBefore (below) sets the health fields and comments; rows with no health at all are skipped. - Run Transform: select BOTH maps (projects, then status). - Done when each pilot project has 1 status report whose colours match Adaptive, and a rerun adds none. (function runTransformScript(source, map, log, target) { var rag = { 'on target': 'green', 'on plan': 'green', 'needs attention': 'yellow', 'in trouble': 'red' }; function c(v) { return rag[(v + '').toLowerCase().trim()] ¦¦ ''; } target.overall_health = c(source.u_health); target.schedule = c(source.u_schedule_health); target.cost = c(source.u_budget_health); target.resources = c(source.u_resource_health); target.scope = c(source.u_scope_health); if (!target.overall_health && !target.schedule && !target.cost && !target.resources && !target.scope) { ignore = true; return; } var risk = source.u_risk_health + ''; var notes = (source.u_update_notes + '').replace(/<[^>]+>/g, ' ').replace(/&nbsp;/g, ' '); target.comments = (risk ? 'Risk health (Adaptive): ' + risk + '\n' : '') + notes; })(source, map, log, target); Adaptive value ¦ project_status value On Target / On Plan ¦ green Needs Attention ¦ yellow In Trouble ¦ red blank ¦ (empty) | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Adaptive keeps health on the project itself (Health, Schedule/Budget/Resource/Scope/Risk Health, Update Notes), so no extra API call is needed: a SECOND transform map on the same staging table u_import_adaptive_projects creates one status report per project. Asana: no status reports for HR portfolio items (they are tasks); not in scope.</p> <ul style="list-style-position: inside;"><li>System property x_mig.status_as_on (string, yyyy-MM-dd) = the migration date, e.g. 2026-10-30. Fixed date = reruns update instead of adding reports.</li><li>New transform map &#x27;Import Adaptive Status Reports&#x27; : u_import_adaptive_projects -&gt; project_status, Order 200 (runs after the project map, Order 100).</li><li>Field map 1: [Script] -&gt; project, Coalesce = true: answer = sys_id of pm_project whose correlation_id = source.u_correlation_id.</li><li>Field map 2: [Script] -&gt; as_on, Coalesce = true: answer = gs.getProperty(&#x27;x_mig.status_as_on&#x27;).</li><li>onBefore (below) sets the health fields and comments; rows with no health at all are skipped.</li><li>Run Transform: select BOTH maps (projects, then status).</li><li>Done when each pilot project has 1 status report whose colours match Adaptive, and a rerun adds none.</li></ul> <pre><code>(function runTransformScript(source, map, log, target) { var rag = { &#x27;on target&#x27;: &#x27;green&#x27;, &#x27;on plan&#x27;: &#x27;green&#x27;, &#x27;needs attention&#x27;: &#x27;yellow&#x27;, &#x27;in trouble&#x27;: &#x27;red&#x27; }; function c(v) { return rag[(v + &#x27;&#x27;).toLowerCase().trim()] ¦¦ &#x27;&#x27;; } target.overall_health = c(source.u_health); target.schedule = c(source.u_schedule_health); target.cost = c(source.u_budget_health); target.resources = c(source.u_resource_health); target.scope = c(source.u_scope_health); if (!target.overall_health &amp;&amp; !target.schedule &amp;&amp; !target.cost &amp;&amp; !target.resources &amp;&amp; !target.scope) { ignore = true; return; } var risk = source.u_risk_health + &#x27;&#x27;; var notes = (source.u_update_notes + &#x27;&#x27;).replace(/&lt;[^&gt;]+&gt;/g, &#x27; &#x27;).replace(/&amp;nbsp;/g, &#x27; &#x27;); target.comments = (risk ? &#x27;Risk health (Adaptive): &#x27; + risk + &#x27;\n&#x27; : &#x27;&#x27;) + notes; })(source, map, log, target);</code></pre> <table style="width: 100%;"><thead><tr><td><strong>Adaptive value</strong></td><td><strong>project_status value</strong></td></tr></thead><tbody><tr><td>On Target / On Plan</td><td>green</td></tr><tr><td>Needs Attention</td><td>yellow</td></tr><tr><td>In Trouble</td><td>red</td></tr><tr><td>blank</td><td>(empty)</td></tr></tbody></table>
STRY0066702 | C | Resource assignments: who works on each task | 3 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Scope: put the people on the tasks (assigned_to + additional_assignee_list). Full Resource Management (resource plans / allocations) is NOT in this story (decision D2). Rate models are removed unless time is loaded as time cards (decision D3). - Adaptive: Data Source 'Adaptive Resources - API' (STRY0067506) loads one row per resource link with Project Correlation ID = the work item (task or project) and Resource Email. - Transform map u_import_adaptive_resources -> pm_project_task, coalesce on correlation_id = the task's correlation id (field map [Script] -> correlation_id returning source.u_project_correlation_id). - onBefore: first resource on a task -> assigned_to; further resources are added to additional_assignee_list (no duplicates). Users matched on email; no match -> logged, left blank. - Links whose work item is a project (ADAPTIVE:/Project/...) update additional_assignee_list on pm_project. - Asana: no separate feed - assignee and followers already come with the Work Plan (NEW-11/NEW-12). - Done when the pilot tasks show the same people as Adaptive. | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Scope: put the people on the tasks (assigned_to + additional_assignee_list). Full Resource Management (resource plans / allocations) is NOT in this story (decision D2). Rate models are removed unless time is loaded as time cards (decision D3).</p> <ul style="list-style-position: inside;"><li>Adaptive: Data Source &#x27;Adaptive Resources - API&#x27; (STRY0067506) loads one row per resource link with Project Correlation ID = the work item (task or project) and Resource Email.</li><li>Transform map u_import_adaptive_resources -&gt; pm_project_task, coalesce on correlation_id = the task&#x27;s correlation id (field map [Script] -&gt; correlation_id returning source.u_project_correlation_id).</li><li>onBefore: first resource on a task -&gt; assigned_to; further resources are added to additional_assignee_list (no duplicates). Users matched on email; no match -&gt; logged, left blank.</li><li>Links whose work item is a project (ADAPTIVE:/Project/...) update additional_assignee_list on pm_project.</li><li>Asana: no separate feed - assignee and followers already come with the Work Plan (NEW-11/NEW-12).</li><li>Done when the pilot tasks show the same people as Adaptive.</li></ul>
NEW-13 | C | Time entries: actual effort per task (Option A, recommended) | 3 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Decision D3. Option A (this story): carry total hours already worked onto each task, so actuals are not lost. Option B (time cards per user per week, with rate models) adds cost records, approvals and fiscal periods; only if the client needs timesheet history in ServiceNow. - Adaptive: Data Source 'Adaptive Time - API' (STRY0067506) on entity [CONFIRM] (e.g. Timesheet), fields [CONFIRM] (reported by, work item, date, duration). - Its script sums hours per work item before inserting: one staging row per task with Project Correlation ID (= the task) and Total Hours. - Transform -> pm_project_task, coalesce via [Script] -> correlation_id = source.u_project_correlation_id; Total Hours -> the task's Actual effort field (dev confirms the field name in the pm_project_task dictionary). - Asana: only if Discovery shows actual_time_minutes; then the Work Plan script also fills Total Hours (minutes / 60). - Done when pilot task actual effort equals the Adaptive totals (spot-check 5 tasks). | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Decision D3. Option A (this story): carry total hours already worked onto each task, so actuals are not lost. Option B (time cards per user per week, with rate models) adds cost records, approvals and fiscal periods; only if the client needs timesheet history in ServiceNow.</p> <ul style="list-style-position: inside;"><li>Adaptive: Data Source &#x27;Adaptive Time - API&#x27; (STRY0067506) on entity [CONFIRM] (e.g. Timesheet), fields [CONFIRM] (reported by, work item, date, duration).</li><li>Its script sums hours per work item before inserting: one staging row per task with Project Correlation ID (= the task) and Total Hours.</li><li>Transform -&gt; pm_project_task, coalesce via [Script] -&gt; correlation_id = source.u_project_correlation_id; Total Hours -&gt; the task&#x27;s Actual effort field (dev confirms the field name in the pm_project_task dictionary).</li><li>Asana: only if Discovery shows actual_time_minutes; then the Work Plan script also fills Total Hours (minutes / 60).</li><li>Done when pilot task actual effort equals the Adaptive totals (spot-check 5 tasks).</li></ul>
STRY0067099 | C | Lessons learned: Adaptive -> u_lessons_learned | 3 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Before starting: the implementation team confirms u_lessons_learned has correlation_id. - Data Source 'Adaptive Lessons - API' (STRY0067506 preset): ENTITY = C_PMOLessonsLearned, PROJECT_FIELD = C_RelatedWorkItem. - Transform map -> u_lessons_learned, coalesce u_correlation_id -> correlation_id. - u_project: [Script] = sys_id of pm_project whose correlation_id = source.u_project_correlation_id. - Name -> u_subject; Lesson Type -> u_lesson_type; Topic -> u_topic; Lesson -> u_lesson; ID -> u_name (only if u_name is not auto-numbered). Choice values arrive already flattened ('Business Process'). - Done when the pilot projects' lessons show on the project, and a rerun gives 0 inserts. | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Before starting: the implementation team confirms u_lessons_learned has correlation_id.</p> <ul style="list-style-position: inside;"><li>Data Source &#x27;Adaptive Lessons - API&#x27; (STRY0067506 preset): ENTITY = C_PMOLessonsLearned, PROJECT_FIELD = C_RelatedWorkItem.</li><li>Transform map -&gt; u_lessons_learned, coalesce u_correlation_id -&gt; correlation_id.</li><li>u_project: [Script] = sys_id of pm_project whose correlation_id = source.u_project_correlation_id.</li><li>Name -&gt; u_subject; Lesson Type -&gt; u_lesson_type; Topic -&gt; u_topic; Lesson -&gt; u_lesson; ID -&gt; u_name (only if u_name is not auto-numbered). Choice values arrive already flattened (&#x27;Business Process&#x27;).</li><li>Done when the pilot projects&#x27; lessons show on the project, and a rerun gives 0 inserts.</li></ul>
STRY0066721 | D (blocked) | Budgets -> cost plans (cost_plan) | 5 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Blocked by decision D4: where budgets live in Adaptive (project budget fields or a budget/expense entity - see Discovery), and whether cost plans or demand totals are wanted (not both: cost plans roll up and overwrite totals). - Data Source from the confirmed Adaptive source, one row per project per expense type (Capex/Opex), Correlation ID = 'ADAPTIVE:' + project id + ':' + expense type. - Transform -> cost_plan, coalesce on correlation id; task = pm_project via Project Correlation ID. - Expense type Capex/Opex and resource type map in field map scripts (dev confirms field names in the cost_plan dictionary). - start_date / end_date = project start / end, so ServiceNow builds cost_plan_breakdown per fiscal period. Fiscal periods must exist for those dates. - Done when pilot project totals in ServiceNow equal Adaptive. | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Blocked by decision D4: where budgets live in Adaptive (project budget fields or a budget/expense entity - see Discovery), and whether cost plans or demand totals are wanted (not both: cost plans roll up and overwrite totals).</p> <ul style="list-style-position: inside;"><li>Data Source from the confirmed Adaptive source, one row per project per expense type (Capex/Opex), Correlation ID = &#x27;ADAPTIVE:&#x27; + project id + &#x27;:&#x27; + expense type.</li><li>Transform -&gt; cost_plan, coalesce on correlation id; task = pm_project via Project Correlation ID.</li><li>Expense type Capex/Opex and resource type map in field map scripts (dev confirms field names in the cost_plan dictionary).</li><li>start_date / end_date = project start / end, so ServiceNow builds cost_plan_breakdown per fiscal period. Fiscal periods must exist for those dates.</li><li>Done when pilot project totals in ServiceNow equal Adaptive.</li></ul>
STRY0066723 | E - last | Attachments: copy files from Asana and Adaptive via the API | 5 | Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the 'Adaptive Projects - API' Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = "ADAPTIVE:" + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or "ASANA:" + Asana gid. Scripts are in the repo folder servicenow/. Replaces the manual download/upload. Runs LAST, after every record exists. Script: servicenow/attachments_fix_script.js (Fix Script). - Asana: GET /attachments?parent=<gid> per migrated record. Files hosted by Asana are downloaded from download_url (short-lived signed link, fetched without the token) and saved to the record (RESTMessageV2.saveResponseBodyAsAttachment). Google Drive / Box / Dropbox / OneDrive files cannot be downloaded: their link is added as a work note. - Adaptive: files linked to the work item, query and download path [CONFIRM] from Discovery (set ADAPTIVE_LINK_QUERY and ADAPTIVE_DOWNLOAD at the top of the script). - Tables: pm_project, pm_project_task, dmn_demand (+ risk, issue once loaded). - Run 1 with DRY_RUN = true: System Logs (source x_mig.attachments) lists what would be copied. Then DRY_RUN = false. - Re-run safe: a file with the same name already on the record is skipped. Files over MAX_MB (50) are logged for manual copy. - Done when the final log line shows failed = 0 (or each failure is listed and handled), and a spot-check of 10 files opens correctly. | <p>Built on what is proven in Dev: system properties x_mig.adaptive.url / x_mig.adaptive.key / x_mig.asana.token / x_mig.asana.project_gid, and the &#x27;Adaptive Projects - API&#x27; Data Source (PRJ0010675 loaded from the API). Keys: correlation_id = &quot;ADAPTIVE:&quot; + Adaptive id (e.g. ADAPTIVE:/Project/5afh...) or &quot;ASANA:&quot; + Asana gid. Scripts are in the repo folder servicenow/.</p> <p>Replaces the manual download/upload. Runs LAST, after every record exists. Script: servicenow/attachments_fix_script.js (Fix Script).</p> <ul style="list-style-position: inside;"><li>Asana: GET /attachments?parent=&lt;gid&gt; per migrated record. Files hosted by Asana are downloaded from download_url (short-lived signed link, fetched without the token) and saved to the record (RESTMessageV2.saveResponseBodyAsAttachment). Google Drive / Box / Dropbox / OneDrive files cannot be downloaded: their link is added as a work note.</li><li>Adaptive: files linked to the work item, query and download path [CONFIRM] from Discovery (set ADAPTIVE_LINK_QUERY and ADAPTIVE_DOWNLOAD at the top of the script).</li><li>Tables: pm_project, pm_project_task, dmn_demand (+ risk, issue once loaded).</li><li>Run 1 with DRY_RUN = true: System Logs (source x_mig.attachments) lists what would be copied. Then DRY_RUN = false.</li><li>Re-run safe: a file with the same name already on the record is skipped. Files over MAX_MB (50) are logged for manual copy.</li><li>Done when the final log line shows failed = 0 (or each failure is listed and handled), and a spot-check of 10 files opens correctly.</li></ul>

## Run order
Step | Data Source | Transform map | Note
1 | Adaptive Projects - API | Import Adaptive Projects Transform Map + Import Adaptive Status Reports
2 | Asana Portfolio - API | Import Asana HR Project Portfolio Transform Map
3 | Adaptive Tasks - API, then Adaptive Milestones - API | Import Adaptive Project Tasks Transform Map | Transform twice
4 | Asana Work Plan - API | Import Asana Project Tasks Transform Map | Transform twice
5 | Adaptive Resources - API | Resources -> pm_project_task
6 | Adaptive Time - API | Time -> pm_project_task (actual effort)
7 | Adaptive Risks - API, Adaptive Issues - API | Existing Risks / Issues maps
8 | Adaptive Lessons - API | Lessons -> u_lessons_learned
9 | (cost plans, when unblocked) | Budgets -> cost_plan
10 | attachments_fix_script.js | (Fix Script, DRY_RUN first) | Always last

## Decisions
# | Decision (BA) | Story
D1 | Adaptive task states: Draft/Requested/On Hold -> Pending, Active -> Work in Progress, Completed -> Closed Complete, Cancelled -> Closed Incomplete. Approve or change. | NEW-12
D2 | Full Resource Management (resource plans/allocations) in scope, or task assignees only? | STRY0066702
D3 | Time: Option A (actual effort totals per task) or Option B (weekly time cards + rate models)? | NEW-13
D4 | Budgets: where they live in Adaptive, and cost plans vs demand totals. | STRY0066721
D5 | Status report date (x_mig.status_as_on): migration date? | STRY0066701
D6 | Planned Finish blank: use Adaptive DueDate instead? | Adaptive Projects - API